## Project_Work_Order6390174052655
Project Work Order
From 19 Nov 2000 To 20 Dec 2025
Page 1 of 1
Total Records: 29 Records 1 To 29
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per | Budget_Head | WO_Completion_Date
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Spider Glazing System | Suspended Spider Glazing System | Sqm | 1201.93 | 5330.89 | 6407356.62 | 1153324.2 | 7560680.82 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1201.93 | 7560680.82 | Design, Fabrication, Supply, Installation, Protection, Cleaning & Handover of Suspended Spider Glazing System, custom designed to with stand the Design wind pressure of 1.48 Kpa conforming to IS -875 part III. ( the system must pass the proof test at 1.5 times design wind pressure). The suspended glazing system shall be of Stainless steel 1 way, 2 way and 4 way spiders & SS fin bracket of grade 316 from (Dorma / Ozone / Equivalent) of SS polished finish assembly supported on Glass fin of 17.52 mm Thick. held by SS Bracket, SS Splice Plate all in line with Tender Drawing. Face Glass shall be 13.52 mm thick Clear laminated Glass. Design shall accommodate floor movement of 20 mm at the at Top and bottom & rate shall include with SS 316 grade fasteners and SS bolts with dome nut of approved make, Clear weather sealants for groove of Dow Corning DC 991 or approved make, teflon/ nylon bushes & separators to prevent bi-metallic contacts, all in complete required to perform as per specification and drawing in conjunction with BOQ. The Top, Bottom & sides of Glass Facade shall be fixed by Aluminium Extruded Channel & Weather Sealant & Backer rod of appoved make with the help of SS 316 grade Screw and shop partition wall gap to be closed, all in line with tender drawing. Rate shall include fin glass as mentioned below glass specification. The extruded Aluminum Sections of Alloy 6063 T6 and tolerances , flatness, twist , bend and angularity confirming to DIN standard from approved extruder. All the visible surfaces shall have Powder Coating with a minimum thickness of 60 to 70 microns and 25 years warranty, shade shall be as per Clients and Architect requirement. The non visible aluminum surfaces shall have minimum chromatizing treatment. The quote rate shall include all design, engineering, shop drawing approval from Architect & consultant, Scaffolding and statutory obligations and safety code compliance as per client. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall Glazing | Top Hung window W/o Glass | SQM | 70 | 5878.88 | 411521.6 | 74073.88 | 485595.48 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 70 | 485595.48 | Design, Fabrication, Installation, Protection, Cleaning and Handover of Top Hung Window. Outer/Shutter panels shall be Top hung openable with multi four point locking system with Friction type hinges ( Window opening will be restricted to 15 deg. ) and necessary hardware of approved make (Caldwell / GU/ Equivalent). (The quote rate shall Include Window frame, Hardware and Accessories) |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall | Ventilation Z Louvers | Sqm | 45 | 2690 | 121050 | 21789 | 142839 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 45 | 142839 | Design, Supply, Fabrication, Installation, Protection, Cleaning & Handover of Aluminum Louvers of " Z " shape and equally spaced. Louver's shall be Supported on Aluminium Tube with Aluminium Flate Bar with required opening for Exhaust fan all in line with the Tender Drawing. Rate Shall include Aluminium mesh, required Amuminium cleat, channel, screw etc. for Ventilation with necessary accessories. The Extruded Aluminium Sections of Alloy 6063 T6 & tolerances conforming to DIN / EN standard from approved extruder. All the visible surfaces shall have Powder Coated (RAAL 7022) with 60 to 80 micron and 10 years warranty, shade as per Clients and Architect requirement. The non visible Aluminium surfaces shall have minimum chromatizing treatment. System shall be designed to withstand Wind Pressure of the 1.48 Kpa. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Sliding Windows (Aluminium) Aluminium Sliding Windows/ Doors | Three Track Aluminum Sliding Door | SQM | 4325 | 3314.93 | 14337072.25 | 2580673 | 16917745.25 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 4325 | 16917745.25 |  |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Sliding Windows (Aluminium) | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Fabrication Glass Canopy | Laminated Glass 13.52 mm | Sqm | 47.2 | 4025 | 189980 | 34196.4 | 224176.4 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 47.2 | 224176.4 | 13.52mm thick Laminated (6mm thick Clear Glass + 1.52mm thick Sentry glas plus + 6mm thick Clear Glass both glass with heat soak) |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Fabrication | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Fabrication Glass Canopy | MS Support System | Kg | 2000 | 210 | 420000 | 75600 | 495600 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 2000 | 495600 | Rate shall include Design, supply & installation MS structure with Tie member between the RCC beam / Steel Structure and Canopy System. All extruded Mild steel sections shall comply to IS 2062 Grade A and shall be coated with antirust primer with PU Paint. The MS support structure shall be designed for complete Wind load, Dead load and Live Load. All sections shall be Tata sections with YST (Yield Strength) 310MPa OR Equivalent. Rate shall include necessary base plate / brackets, fastening straps, nuts, bolts, rivets, washers, Microwave Cured EPDM / Neoprene barrier, Thermal Isolator and other fastening materials shall be in stainless steel grade 316. All Anchor fastener should be SS grade 316 Make- Hilti. The steel structure shall be finish with the following, i. Surface Preparation Rate shall include Design, supply & installation MS structure with Tie member between the RCC beam / Steel Structure and Canopy System. All extruded Mild steel sections shall comply to IS 2062 Grade A and shall be coated with antirust primer with PU Paint. The MS support structure shall be designed for complete Wind load, Dead load and Live Load. All sections shall be Tata sections with YST (Yield Strength) 310MPa OR Equivalent. Rate shall include necessary base plate / brackets, fastening straps, nuts, bolts, rivets, washers, Microwave Cured EPDM / Neoprene barrier, Thermal Isolator and other fastening materials shall be in stainless steel grade 316. All Anchor fastener should be SS grade 316 Make- Hilti. The steel structure shall be finish with the following, i. Surface Preparation |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Fabrication | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Fabrication Glass Canopy | Suspended Glass Canopy | Sqm | 47.2 | 7187.06 | 339229.23 | 61061.26 | 400290.49 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 47.2 | 400290.49 | Design, Supply, Fabrication, Installation, Protection, Cleaning & Handover of Suspended Glass Canopy (Spider) with Tie Rod, custom designed to with stand the Design wind pressure of 1.48 Kpa conforming to IS -875 part III. ( the system must pass the proof test at 1.5 times design wind pressure). The Canopy system shall be of Stainless steel 1 way, 2-way and 4 way spiders (With hole in Glass) of grade 316 from Ozone / Equivalent of SS polished finish assembly supported on M.S. Structure all in line with Tender Drawing. Canopy Glass shall be 13.52 mm Thick. laminated Toughened Glass. Rate Shall include SS 316 grade fasteners and anchor bolts of approved make, weather sealants of Dowsil for (filling the glass groove) or approved make, teflon/ nylon bushes & separators to prevent bi-metallic contacts, MS Prop all in complete required to perform as per specification and drawing in conjunction with BOQ. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Fabrication | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall | 8 mm thick clear HS glass | Sqm | 562.32 | 1207 | 678720.24 | 122169.64 | 800889.88 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 562.32 | 800889.88 | Extra over and above cost item, 8mm Thick clear glass HS |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment ACP Cladding | ACP Cladding - System | SQM | 804.75 | 3110.09 | 2502844.93 | 450512.08 | 2953357.01 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 804.75 | 2953357.01 | Design, Fabrication, Installation, Protection, Cleaning and Handover of ACP Cladding comprises of 4mm Thick. Aluminium composite panels (ACP) cladding system of approved shade & make fixed on to the Extruded aluminium section framing (Vertical and Horizontal) mechanically fixed on to the designed RCC using Hot Dip Galvanised HDG-80 microns MS brackets with the help of SS 316 Grade Anchor Fasteners all in line with Tender Drawing. Fabricated Aluminium composite panels (ACP) with grooving and bending along with corner cleats are mechanically fixed to the aluminium framing using extruded aluminium cleats and stainless steel 316 grade screws. The vertical/horizontal joints are to be sealed with weather silicone (DC 991) & backer rod of approved make. The ACP panel & Aluminium Framing shall be done all in line with the Tender Drawing. The system shall be designed to withstand a wind pressure of 1.48 KPa as per IS 875 part 3 at all levels, elevations and heights. The extruded aluminium sections shall be of 6063 T6 alloy or BSH9 Conforming to IS- 63400. Rate shall include providing: Fabrication and fixing of ACP cladding along with its framing members and accessories of specified make. The fastening materials like Nuts, Bolts, Rivets, washers, clamps, straps etc along with all consumables and accessories required for fixing the ACP cladding system shall be of stainless steel 316 grade of approved make as per architects/Consultants Specification. Exterior perimeter sealants (DC 991) & backer Rod at the junctions of adjacent materials to the ACP cladding. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment ACP Cladding | ACP Cladding- 4mm Thick - FR Grade ACP Sheet | SQM | 804.75 | 2173.5 | 1749124.13 | 314842.34 | 2063966.47 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 804.75 | 2063966.47 | Quote rate include Aluminium Composite Panel shall be of approved makes & made out of 4mm thk. Aluminium composite panel comprising of Aluminium Skin of Min. 0.5mm (Alloy Grade AA3105) with KYNAR 500/Hylar 5000 PVDF based fluorocarbon / FEVE Lumiflon paint based fluro-polymer resin/Exterior Grade Lead free Coating on Top Face Compliance to AAMA 2605 of approved finish + 3mm thk. noncombustible mineral based polymer core compliance to Class "B" As per BS 476 & 2 hrs Fire Resistance as per ASTM E119 & NBC Guidlines 2016 + 0.5mm aluminium skin with service coat on Bottom face. Overall weight of the ACP shall not be less than 7.0 kg per sq.mtr. ACP Shade Dark Grey TMX-6001 MISTY GREY as approved by Client / Architect. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Aluminium Perforated Cladding | Aluminium Perforated Cladding | Sqm | 4610.7 | 5105.47 | 23539790.53 | 4237162.3 | 27776952.83 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 4610.7 | 27776952.83 | Design, Supply, Fabrication, Installation, Protection, Cleaning and Handover of 3mm thick Aluminium Perforated fabricated (Alloy 3004-H34) shall be fixed on Aluminium extruded section Framing (Alloy 6063 T6) all in line with Tender Drawings. The system should be designed to withstand the Wind Pressure of 1.48 Kpa conforming to IS 875 part III (the system must pass the proof test at 1.5 times designed wind pressure without any failure, permanent deformation). Aluminium Solid cladding should be fixed using screws all in line with Tender Drawings. Aluminium frame work shall be fixed on RCC/MS Structure with the help of M. S. Brackets Hop Dip Galvanised upto 80 microns, with Grade 316 SS Fasteners, SS bolts and nuts, Screw, complete with all other necessary accessories. All the vertical/horizontal joints are to be sealed with weather silicone (DC 991) & backer rod of approved make. The extruded Aluminum Sections of Alloy 6063 T6 and tolerances , flatness, twist , bend and angularity conforming to DIN standard from approved extruder. All the visible surfaces of Aluminium perforated should be Super Durable Coating with 60 to 80 microns and 25 years warranty, shade shall be Dark Grey shade code will be as per Clients and Architect |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Aluminium Vertical Louvers | Aluminium Vertical Louvers (L+M) | Sqm | 1327.44 | 5634 | 7478796.96 | 1346183.46 | 8824980.42 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1327.44 | 8824980.42 | The fastening materials like Nuts, Bolts, Screws, Rivets, washers, clamps, straps etc along with all consumables and accessories required for fixing the Metal cladding system shall be of brushed stainless steel 316 grade and corrosion resistant of approved make as per architects/Consultants Specification. Weather silicone shall be applied as per shown in drawing Exterior perimeter sealants (DC 991) & Backer Rod at the junctions of adjacent materials to the Metal cladding. The extruded Aluminum Sections of Alloy 6063 T6 and tolerances , flatness, twist , bend and angularity conforming to DIN standard from approved extruder. All the visible surfaces of Louvers with system & Aluminium Mesh shall have Silver Anodized with a minimum thickness of 25 microns and 10 years warranty, shade shall be as per Clients and Architect requirement. The non visible aluminium surfaces shall have minimum chromatizing treatment. The quote rate shall include all design, engineering, shop drawing approval from Architect & consultant, Scaffolding and statutory obligations and safety code compliance as per client. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Aluminium Z Louvers | Aluminium Z Louvers | Sqm | 1.44 | 3766 | 5423.04 | 976.14 | 6399.18 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1.44 | 6399.18 | Design, Supply, Fabrication, Installation, Protection, Cleaning & Handover of Aluminum Louvers of " Z " shape and equally spaced. Louver's shall be Supported on Aluminium Tube with Aluminium Flate Bar with side hung openable all in line with the Tender Drawing. Rate Shall include Aluminium mesh, required Amuminium cleat, channel, screw etc. for Ventilation with necessary accessories. The Extruded Aluminium Sections of Alloy 6063 T6 & tolerances conforming to DIN / EN standard from approved extruder. All the visible surfaces shall have Powder Coated (RAAL 9022) with 60 to 80 micron and 10 years warranty, shade as per Clients and Architect requirement. The non visible Aluminium surfaces shall have minimum chromatizing treatment. System shall be designed to withstand Wind Pressure of the 1.48 Kpa. All necessary fasteners of SS 316 grade in line with Tender Drawing with stainless steel Anchor fasteners/ Bolts, Teflon separator to prevent bimetallic contacts with nuts and washers etc. of stainless steel Grade 316. All the Periphery joints horizontal or vertical inside and outside proper sealed with weather sealants during the installation (DC-789) & backer Rod of approved make with shade by Client / Architect. The quote rate shall include all design, engineering, shop drawing approval from Architect & consultant, Scaffolding and statutory obligations and safety code compliance as per client. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall Glazing | Curtain wall System (L+M) | SQM | 1411.74 | 4364.7 | 6161821.58 | 1109127.88 | 7270949.46 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1411.74 | 7270949.46 | The scope is to Design, Supply, Fabrication, Installation, Protection, Cleaning and Handover of Conventional Curtain wall system designed to withstand a Design wind pressure of 1.48 Kpa conforming to IS 875 Part-lll (the system must pass the proof test at 1.5 times designed wind pressure without any failure, permanent deformation) and fabricated fixed at all levels, elevation and heights. The Glass panels will be mechanically supported to the Aluminium main frame with pressure plate & cover cap from both side and fixed onto mullions and transoms with all approved standard accessories and hardware |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | Finishing Work | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall | Curtain wall System (L+M) | SQM | 607.32 | 4364.7 | 2650769.6 | 477138.52 | 3127908.12 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 607.32 | 3127908.12 | The scope is to Design, Supply, Fabrication, Installation, Protection, Cleaning and Handover of Conventional Curtain wall system designed to withstand a Design wind pressure of 1.48 Kpa conforming to IS 875 Part-lll (the system must pass the proof test at 1.5 times designed wind pressure without any failure, permanent deformation) and fabricated fixed at all levels, elevation & heights. The Glass panels will be mechanically supported to the Aluminium main frame with pressure plate & cover cap from both side and fixed onto mullions and transoms with all approved standard accessories and hardward?s of approved make all in line with the Tender Drawing. Rate shall include Aluminium Adoptor /Tube with Accenssories of SS 316 Grade all in line with the Tender Drawing. Rate shall include fixing of the main frames to RCC with necessary HDG MS bracket, fastening straps, nuts, bolts, rivets, washers and other fastening materials shall be in stainless steel grade 316 all in line with Tender Drawing. Rate shall include Microwave Cured EPDM / Neoprene barrier complete for a full proof system all in line with Tender Drawing. Providing and Fixing Ethylene Propylene Dinine Monomer (EPDM) Gaskets as weather strip and barrier to ensure water and air tightness. Weather strip shall be EPDM Gaskets with Hardness (5 second) shore A with a typical value not less than 65, ultimate tensile strength of 70 (+/- 10%) Kg/Sq.cm and ultimate elongation of 250% (+/- 10%). Fabricating and supplying Mild Steel (Hot Dip Galvanized 80 microm thick) Brackets to accommodate 3 Dimensional movement for achieving perfect verticality and proper fixing of structural glazing system with the RCC / masonry / structural steel framework of building structure, using stainless steel Grade 316 anchor fasteners ( Klimas/Hilti ) / bolts, Teflon separator to prevent bimetallic contacts with nuts and washers etc. of stainless steel Grade 316, of the required capacity and in required numbers. The extruded Aluminum Sections of Alloy 6063 T6 and tolerances , flatness, twist , bend and angularity conforming to DIN standard from approved extruder. All the visible surfaces shall have Powder Coating (RAAL 7022) with a minimum thickness of 60 to 80 microns and 10 years warranty, shade shall be as per Clients and Architect requirement. The non visible aluminum surfaces shall have minimum chromatizing treatment. The rate shall include closure of 1.5 mm Aluminum visible and non visible 1mm thick GI primary seal with Insulation at periphery of the Glazing and End closure with wall/column all in line with the Tender Drawing. The Flashing fixed with the help of Aluminium Cleat by SS pan head screw all in line with the Tender Drawing. All the visible surfaces shall have Powder Coating (RAAL 7022) with a minimum thickness of 60 to 80 microns and 10 years warranty, shade shall be as per Clients and Architect requirement. Rate shall include necessary clamps / brackets, fastening straps, Screws, rivets, washers and other fastening materials shall be in stainless steel grade 316. Gap between RCC & flashing filled with Backer rod & Weather Sealant (DC 991) of approved make. The quote rate shall include all design, engineering, shop drawing approval from Architect & consultant, Scaffolding and statutory obligations and safety code compliance as per client. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | Finishing Work | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Spider Glazing System | Double leaf Patch fitting Door | SQM | 18.72 | 5425.73 | 101569.67 | 18282.54 | 119852.21 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 18.72 | 119852.21 | Fabrication, Installation, Protection, Cleaning & Handover of Patch fitting Framless Double/ Single leaf Door fitted with floor spring, pivot, lock set ,handle ( 25 mm dia. and c/c 600 mm ) or any other hardware requirement to complete the assembly. All the hardware and accessories shall be of Ozone or equivalent make as approved by Architect. All the assembly for the door shall be designed to windstand all the load and as recommended by the supplier. The Contractor must quote rates accordingly. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Aluminium Sliding Windows/ Doors (L+M) | Extra over rate for toughened Glass - 6mm to 8mm | SQM | 4325 | 250 | 1081250 | 194625 | 1275875 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 4325 | 1275875 |  |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Stone Cladding | Granite (M) | Sq.Mtr | 2353.74 | 1331.27 | 3133463.45 | 564023.42 | 3697486.87 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 2353.74 | 3697486.87 | 20mm Thick. Granite Rajasthan Black Granite-finish with three option - Leather Finish Nero Magic Granite, Flaming plus River Wash Finish, & Flaming Finish (Approved by Client / Architect.) |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Stone Cladding | MS Support System | Kg | 17500 | 150 | 2625000 | 472500 | 3097500 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 17500 | 3097500 | All extruded Mild steel sections & Base plate shall comply to IS 2062 Grade A and all MS Structure shall be (Hot Dip Galvanized 80 micron). The MS support structure shall be designed for complete wind load, Dead load and Live Load. Mild steel section fixed with RCC using stainless steel anchor fasteners of stainless steel Grade 316 of the required capacity and in required numbers. All the Sections shall be YST 310 MPA or Equivalent all in line with Tender Drawing. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment ACP Cladding | MS Support System | Kg | 3500 | 150 | 525000 | 94500 | 619500 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 3500 | 619500 | All extruded Mild steel sections & Base plate shall comply to IS 2062 Grade A and all MS Structure shall be (Hot Dip Galvanized 80 micron). The MS support structure shall be designed for complete wind load, Dead load and Live Load. Mild steel section fixed with RCC using stainless steel anchor fasteners of stainless steel Grade 316 of the required capacity and in required numbers. All the Sections shall be YST 310 MPA or Equivalent all in line with Tender Drawing. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Aluminium Sliding Windows/ Doors (L+M) | Providing & Fixing Two Track Window-M+L | SQM | 885 | 2989.07 | 2645326.95 | 476158.86 | 3121485.81 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 885 | 3121485.81 | Design, Supply, Fabrication, Installation, Protection, Cleaning and Handover Sliding Door (27MM) EURO Series both side opening comprising SGU Glass. All extruded Aluminum profiles to withstand a Wind Pressure of 1.48 Kpa conforming to IS 875 part III (the system must pass the proof test at 1.5 times designed wind pressure without any failure, permanent deformation) shall be conforming to alloy 6063 T6 all in line with the Tender Drawing. The Contractor shall follow the Conceptual System for rates. Rate shall include Aluminum Reinforcement profile at interlock location all in line with Tender Drawing. Rate Shall include the Sliding Shutter will Slide on (2Track with 2 glass shutter) approved quality of Nylon Rollers (double Adjustable Roller for Window) and Concealed sliding Lock (Make : Cotswold / Giesse / Sobinco / Equivalent) . The Window accessories include Polymaide Wool Pile, Dust Pad, Shutter guide and Drainage Cap of approved make. All the joints horizontal or vertical inside and outside proper sealed with weather sealants (Non Stain & Non-bleed) during the installation (DC-991) of approved make with shade by Client / Architect. Bottom track should not be drilled or punchered for fixing the RCC slab for fixing the bottom track, Polyamide block should be fixed on RCC slab all in line with tender drawing. The System and Glass designed to withstand Wind Pressure of maximum 1.48 KPA conforming to IS 875 Part-lll (the system must pass the proof test at 1.5 times designed wind pressure without any failure, permanent deformation) and fabricated fixed at all levels, elevation & heights. The extruded Aluminum Sections of Alloy 6063 T6 and tolerances , flatness, twist , bend and angularity conforming to DIN standard from approved extruder. All the Visible Surfaces shall have Powder Coated (RAAL 7022) with a minimum thickness of 60 to 80 microns and 10 years warranty, shade shall be as per Clients and Architect Requirement. The window shall be sealed to the host structure and not adjoining materials with approved water proofing membrane. Rate shall include necessary fastening straps, Screws, rivets, washers and other fastening materials shall be in (Klimas KPL FAST SQ-Ceramic). Seal Exterior perimeter with Dow Corning DC 991 & Backer Rod of Approved make & Shade, where the System abuts other adjacent materials such as concrete shear walls. The Contractor must fabricate & installed the system as per the prevalent site conditions and building elevation profiles. No Extra claims shall be entertained at any stage for Aluminum profile/sheet wall thickness and Size Dimensions. Providing and Fixing Ethylene Propylene Dinine Monomer (EPDM) Gaskets as weather strip and barrier to ensure water and air tightness. Weather strip shall be EPDM Gaskets with Hardness (5 seconds) shore A with a typical value not less than 65, ultimate tensile strength of 70 (+/- 10%) Kg/Sq.cm and ultimate elongation of 250% (+/- 10%). GLASS SPECIFICATION, For Extra over and above cost item no. B.1 & B.2 6mm Thick clear Toughened glass |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall Glazing | SGU Glass (10mm thk) (L+M) | Sqm | 151.68 | 1725 | 261648 | 47096.64 | 308744.64 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 151.68 | 308744.64 | SGU GLASS FOR DOOR- 10MM THICK CLEAR GLASS FT WITH HEAT SOAK. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall Glazing | SGU Glass (8mm thk) (L+M) | Sqm | 1260.06 | 1207.5 | 1521522.45 | 273874.04 | 1795396.49 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1260.06 | 1795396.49 | SGU GLASS - 8MM THICK CLEAR GLASS HS. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Spider Glazing System | SGU GLASS - 12MM THICK CLEAR GLASS Heat Strengthen | SQM | 59.28 | 2300 | 136344 | 24541.92 | 160885.92 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 59.28 | 160885.92 | SGU Glass For Door- 12mm Thick Clear Glass FT With Heat Hoak. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Spider Glazing System | SHOP FRONT-Laminated Glass - 13.52mm thk | SQM | 1142.65 | 4025 | 4599166.25 | 827849.92 | 5427016.17 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 1142.65 | 5427016.17 | 13.52mm thick Laminated (6mm thick Clear Glass + 1.52mm thick PVB + 6mm thick Clear Glass both glass with heat soak) |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Curtain Wall Glazing | Single leaf Frame Door | SQM | 151.68 | 5919.52 | 897872.79 | 161617.1 | 1059489.89 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 151.68 | 1059489.89 | Design, fabrication, Installation and Handover Single/Double leaf Framed Door opening inward comprising SGU Toughened Glass with SS handle with Lock (Make Cotswold/G-U/ Giesse) as approved by Architect and Client. The System shall be Designed to withstand Wind Pressure of 1.48 kpa. System consist of Aluminum outer, Shutter and Beading Profiles, all in line with Tender Drawing. Hinges Shall be Butt Hinges with Approved make. The Door Accessories includes the wool pile, Epdm Gaskets all in line with the Tender Drawing. All exposed Aluminum profiles shall be Powder Coating (RAAL 7022) with a minimum thickness of 60 to 70 microns and 25 years warranty, shade shall be as per Clients and Architect requirement. The non visible Aluminum Surfaces shall have minimum chromatizing treatment. Provide exterior perimeter sealants with Dow Corning DC 991, where these System abuts other adjacent materials such as concrete shear walls. The quote rate shall include all design, engineering, shop drawing approval from Architect & consultant, Scaffolding and statutory obligations and safety code compliance as per client |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Spider Glazing System | Single leaf patch Door | Sqm | 40.56 | 5425.73 | 220067.61 | 39612.16 | 259679.77 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 40.56 | 259679.77 | Fabrication, Installation, Protection, Cleaning & Handover of Patch fitting Framless Double/ Single leaf Door fitted with floor spring, pivot, lock set ,handle ( 25 mm dia. and c/c 600 mm ) or any other hardware requirement to complete the assembly. All the hardware and accessories shall be of Ozone or equivalent make as approved by Architect. All the assembly for the door shall be designed to windstand all the load and as recommended by the supplier. The Contractor must quote rates accordingly. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment SS Cladding | SS Panel Cladding System | Sqm | 823.2 | 9784.06 | 8054238.19 | 1449762.88 | 9504001.07 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 823.2 | 9504001.07 | Design, Supply, Fabrication, Installation, Protection, Cleaning & Handover of SS Cladding System comprises of 2mm Thick. SS Solid fabricated circular Panel grade 316 of brush Finish approved by Client / Architect make including all necessary frame work all in line with Tender Drawing. The Metal Panel shall be supported on Aluminum Tube Framing with Aluminum Cleat, the System shall be hold by hot dip Galvanized up to 80 micron thick M.S. brackets with Grade 316 SS Fasteners, SS bolts and nuts complete with all other necessary accessories. The non visible aluminum surfaces shall have minimum chromatizing treatment. The Bracket support shall be designed to accommodate 3 Dimensional movement for achieving perfect verticality and proper fixing of Metal Cladding. The rate shall include powder coated aluminium U channel fixed with 3M tape at vertical/horizontal grooves. The system shall be designed to withstand a wind pressure of 1.48 KPa as per IS 875 part 3 at all levels, elevations and heights. The extruded aluminium sections shall be of 6063 T6 alloy or BSH9 Conforming to IS- 63400. The fastening materials like Nuts, Bolts, Screws, Rivets, washers, clamps, straps etc along with all consumables and accessories required for fixing the Metal cladding system shall be of brushed stainless steel 316 grade and corrosion resistant of approved make as per architects/Consultants Specification. Weather silicone shall be applied as per shown in drawing Exterior perimeter sealants (DC 991) & Backer Rod at the junctions of adjacent materials to the Metal cladding. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31
Solitaire Business Hub - III | 65 | 2 | 28 Sep 2023 | ONEDEO LEELA FACADE SYSTEMS PRIVATE LIMITED | Elevation Treatment Stone Cladding | Stone dry cladding System | Sqm | 2353.74 | 2990.86 | 7039706.82 | 1267147.22 | 8306854.04 | 5 | 0 | 0 | -1800 | 0 | 0 | 0 | 2353.74 | 8306854.04 | Design, Supply, Fabrication, Installation, Protection, Cleaning & Handover of 20mm Thick Stone cladding with under cut system designed to withstand the design wind pressure. (The system must pass the proof test at 1.5 times design wind pressure without any failure) color finish of Approved by Client / Architect including all necessary frame work all in line with Tender Drawing. Stone shall be fix on Extruded Aluminium horizontal C channel and C channel to be fix on RCC Structure/MS Stucture using Anchor fastener make SS 316 grade. all other necessary accessories. Auminium C channel shall be perfect horizontly and proper fixing of under cut stone Cladding System. Four anchor fasteners shall be fix for each Stone cladding panel installation. The rate shall include additional MS HDG bracket for Signage board fixing as per structural requirement. The system shall be designed to withstand a wind pressure of 1.48 KPa as per IS 875 part 3 at all levels, elevations and heights. The extruded aluminium sections shall be of 6063 T6 alloy or BSH9 Conforming to IS- 63400 & tolerances, flatness, twist , bend and angularity conforming to DIN standard from approved extruder. The non visible aluminum surfaces shall have minimum chromatizing treatment all in line with tender drawing. The system shall be designed to withstand a wind pressure of 1.48 KPa as per IS 875 part 3 at all levels, elevations and heights. The extruded aluminium sections shall be of 6063 T6 alloy or BSH9 Conforming to IS- 63400 & tolerances, flatness, twist , bend and angularity conforming to DIN standard from approved extruder. The non visible aluminum surfaces shall have minimum chromatizing treatment all in line with tender drawing. The quote rate shall include all Scaffolding and statutory obligations and safety code compliance as per client. |  | Auditor | koustubh | Auditor | Construction | 13 Jun 2025 |  | No category | Approved | Auditor |  | 0 | Elevation Treatment | 2024-01-31