## Project_Work_Order6390174269155
Project Work Order
From 19 Nov 2020 To 20 Dec 2025
Page 1 of 1
Total Records: 90 Records 1 To 90
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per | Budget_Head | WO_Completion_Date
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Staff | April 2025 | Month | 210 | 618.23 | 129828.3 | 23369.1 | 153197.4 | 0 | 197.5 | 122100.43 | 0 | 0 | 21978.08 | 144078.51 | 12.5 | 9118.9 | 7 HK Staff x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 94.0476 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Supervisor | April 2025 | Month | 30 | 757.83 | 22734.9 | 4092.28 | 26827.18 | 0 | 26 | 19703.58 | 0 | 0 | 3546.64 | 23250.22 | 4 | 3576.96 | 1 HK Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 86.6667 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Staff | June 2025 | Month | 210 | 618.23 | 129828.3 | 23369.1 | 153197.4 | 0 | 193 | 119318.39 | 0 | 0 | 21477.32 | 140795.71 | 17 | 12401.69 | 7 HK Staff x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 91.9048 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Supervisor | June 2025 | Month | 30 | 757.83 | 22734.9 | 4092.28 | 26827.18 | 0 | 29.5 | 22355.99 | 0 | 0 | 4024.08 | 26380.07 | 0.5 | 447.12 | 1 HK Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 98.3333 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Staff | May 2025 | Month | 217 | 598.29 | 129828.93 | 23369.2 | 153198.13 | 0 | 198 | 118461.42 | 0 | 0 | 21323.06 | 139784.48 | 19 | 13413.65 | 7 HK Staff x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 91.2442 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 1 | 0 | 21 Jun 2025 | HP Facility Management Services Pvt Ltd | Agencies HK Supervisor | May 2025 | Month | 31 | 733.39 | 22735.09 | 4092.32 | 26827.41 | 0 | 31 | 22735.09 | 0 | 0 | 4092.32 | 26827.41 | 0 | 0 | 1 HK Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2025-09-19
Facility_Montek Land Spaces LLP | 2 | 0 | 21 Jun 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | April 2025 | Month | 204 | 1438.9 | 293535.6 | 52836.4 | 346372 | 0 | 204 | 293535.6 | 0 | 0 | 52836.4 | 346372 | 0 | 0 | 7 Operator x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-09-19
Facility_Montek Land Spaces LLP | 2 | 0 | 21 Jun 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | February 2025 | Month | 21 | 1541.67 | 32375.07 | 5827.52 | 38202.59 | 0 | 21 | 32375.07 | 0 | 0 | 5827.52 | 38202.59 | 0 | 0 | 7 Operator x 28 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-09-19
Facility_Montek Land Spaces LLP | 2 | 0 | 21 Jun 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | June 2025 | Month | 210 | 1438.9 | 302169 | 54390.42 | 356559.42 | 0 | 207 | 297852.3 | 0 | 0 | 53613.42 | 351465.72 | 3 | 5093.7 | 7 Operator x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 98.5714 | AMC | 2025-09-19
Facility_Montek Land Spaces LLP | 2 | 0 | 21 Jun 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | March 2025 | Month | 208 | 1392.48 | 289635.84 | 52134.46 | 341770.3 | 0 | 208 | 289635.84 | 0 | 0 | 52134.46 | 341770.3 | 0 | 0 | 7 Operator x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-09-19
Facility_Montek Land Spaces LLP | 2 | 0 | 21 Jun 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | May 2025 | Month | 224 | 1348.96 | 302167.04 | 54390.06 | 356557.1 | 0 | 224 | 302167.04 | 0 | 0 | 54390.06 | 356557.1 | 0 | 0 | 7 Operator x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-09-19
Facility_Montek Land Spaces LLP | 4 | 0 | 30 Jun 2025 | Swach Plus Seva Shakari Sanstha Maryadit | Agencies Garbage Collection And Disposal Services | Administration Charges | NOS | 3 | 275 | 825 | 148.5 | 973.5 | 0 | 2.909 | 799.98 | 0 | 0 | 144 | 943.98 | 0.091 | 29.53 | Admin Charges From Apr-25 to Jun-25 |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2025-09-28
Facility_Montek Land Spaces LLP | 4 | 0 | 30 Jun 2025 | Swach Plus Seva Shakari Sanstha Maryadit | Agencies Garbage Collection And Disposal Services | Garbage Disposal Monthly Charges | Month | 3 | 2750 | 8250 | 0 | 8250 | 0 | 2.909 | 7999.75 | 0 | 0 | 0 | 7999.75 | 0.091 | 250.25 | Reimbursement Charges - Waste Collection From Apr-25 to Jun-25 |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2025-09-28
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | April 2025 | Month | 150 | 633.33 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 112099.42 | 5 Gardener Manpower x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | April 2025 | Month | 30 | 733.33 | 21999.9 | 3959.98 | 25959.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25959.88 | 1 Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | August 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | August 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | December 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | December 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | February 2026 | Month | 140 | 678.57 | 94999.8 | 17099.96 | 112099.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 112099.76 | 5 Gardener Manpower x 28 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | February 2026 | Month | 28 | 785.71 | 21999.88 | 3959.98 | 25959.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 25959.86 | 1 Supervisor x 28 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | January 2026 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | January 2026 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | July 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | July 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | June 2025 | Month | 150 | 633.33 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 112099.42 | 5 Gardener Manpower x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | June 2025 | Month | 30 | 733.33 | 21999.9 | 3959.98 | 25959.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25959.88 | 1 Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Maintenance of Garden Activity | Maintenance Of Garden Activity | Month | 12 | 10000 | 120000 | 21600 | 141600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 141600 | The maintenance of the garden includes all the activities necessary to keep the garden in good condition, such as weeding, cleaning, daily watering, lawn moving, trimming of hedges, trees, flowers and the application of manure, fertilizers and sprays. This includes the use of tools, insecticides, herbicides and fungicides ( E.g.. Urea, DAP, 19:19:19, Roger and Cannon). |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | March 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | March 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | May 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | May 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | November 2025 | Month | 150 | 633.33 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 112099.42 | 5 Gardener Manpower x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | November 2025 | Month | 30 | 733.33 | 21999.9 | 3959.98 | 25959.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25959.88 | 1 Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | October 2025 | Month | 155 | 612.9 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 112099.42 | 5 Gardener Manpower x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | October 2025 | Month | 31 | 709.67 | 21999.77 | 3959.96 | 25959.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 25959.73 | 1 Supervisor x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Manpower Services | September 2025 | Month | 150 | 633.33 | 94999.5 | 17099.92 | 112099.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 112099.42 | 5 Gardener Manpower x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 7 | 0 | 22 Jul 2025 | Shivkrushna Landscape | Agencies Gardener Supervisor | September 2025 | Month | 30 | 733.33 | 21999.9 | 3959.98 | 25959.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25959.88 | 1 Supervisor x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-10-20
Facility_Montek Land Spaces LLP | 8 | 0 | 01 Aug 2025 | Yashraj Enterprises | AMC WTP Operation Monthly Charges | August 2025 | Month | 1 | 19000 | 19000 | 3420 | 22420 | 0 | 1 | 19000 | 0 | 0 | 3420 | 22420 | 0 | 0 | WTP water Tank Cleaning for the month of Aug.2025 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-10-30
Facility_Montek Land Spaces LLP | 8 | 0 | 01 Aug 2025 | Yashraj Enterprises | AMC WTP Operation Monthly Charges | December 2025 | Month | 1 | 19000 | 19000 | 3420 | 22420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22420 | WTP water Tank Cleaning for the month of Dec.2025 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-10-30
Facility_Montek Land Spaces LLP | 8 | 0 | 01 Aug 2025 | Yashraj Enterprises | AMC WTP Operation Monthly Charges | February 2026 | Month | 1 | 19000 | 19000 | 3420 | 22420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22420 | WTP water Tank Cleaning for the month of Feb.2026 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-10-30
Facility_Montek Land Spaces LLP | 8 | 0 | 01 Aug 2025 | Yashraj Enterprises | AMC WTP Operation Monthly Charges | October 2025 | Month | 1 | 19000 | 19000 | 3420 | 22420 | 0 | 1 | 19000 | 0 | 0 | 3420 | 22420 | 0 | 0 | WTP water Tank Cleaning for the month of Oct.2025 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-10-30
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | August 2025 | Month | 224 | 1348.96 | 302167.04 | 54390.06 | 356557.1 | 0 | 205 | 276536.8 | 0 | 0 | 49776.62 | 326313.42 | 19 | 30243.68 | 7 Operator x 31 Days + 7 PH |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 91.5179 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | December 2025 | Month | 217 | 1392.48 | 302168.16 | 54390.26 | 356558.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 356558.42 | 7 Operator x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | February 2026 | Month | 196 | 1541.67 | 302167.32 | 54390.12 | 356557.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 356557.44 | 7 Operator x 28 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | January 2026 | Month | 224 | 1348.96 | 302167.04 | 54390.06 | 356557.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 356557.1 | 7 Operator x 31 Days + 7 PH |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | July 2025 | Month | 217 | 1392.48 | 302168.16 | 54390.26 | 356558.42 | 0 | 214 | 297990.72 | 0 | 0 | 53638.32 | 351629.04 | 3 | 4929.38 | 7 Operator x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 98.6175 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | March 2026 | Month | 217 | 1392.48 | 302168.16 | 54390.26 | 356558.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 356558.42 | 7 Operator x 31 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 0 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | November 2025 | Month | 210 | 1438.9 | 302169 | 54390.42 | 356559.42 | 0 | 205 | 294974.5 | 0 | 0 | 53095.42 | 348069.92 | 5 | 8489.5 | 7 Operator x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 97.619 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | October 2025 | Month | 224 | 1348.96 | 302167.04 | 54390.06 | 356557.1 | 0 | 221 | 298120.16 | 0 | 0 | 53661.62 | 351781.78 | 3 | 4775.32 | 7 Operator x 31 Days + 7 PH |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 98.6607 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 9 | 0 | 11 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | September 2025 | Month | 210 | 1438.9 | 302169 | 54390.42 | 356559.42 | 0 | 204 | 293535.6 | 0 | 0 | 52836.4 | 346372 | 6 | 10187.42 | 7 Operator x 30 Days |  | Auditor | Armaan.Khan | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 97.1429 | AMC | 2025-11-09
Facility_Montek Land Spaces LLP | 11 | 0 | 16 Aug 2025 | Swach Plus Seva Shakari Sanstha Maryadit | Agencies Garbage Collection And Disposal Services | Administration Charges | NOS | 9 | 275 | 2475 | 445.5 | 2920.5 | 0 | 5 | 1375 | 0 | 0 | 247.5 | 1622.5 | 4 | 1298 | Admin Charges From Jul-25 to Mar-26 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2025-11-14
Facility_Montek Land Spaces LLP | 11 | 0 | 16 Aug 2025 | Swach Plus Seva Shakari Sanstha Maryadit | Agencies Garbage Collection And Disposal Services | Garbage Disposal Monthly Charges | Month | 9 | 2750 | 24750 | 0 | 24750 | 0 | 5 | 13750 | 0 | 0 | 0 | 13750 | 4 | 11000 | Reimbursement Charges - Waste Collection From Jul-25 to Mar-26 |  | Auditor | Dhananjay Dhoke | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2025-11-14
Facility_Montek Land Spaces LLP | 15 | 0 | 18 Aug 2025 | Thermax Limited | AMC WTP Operation Monthly Charges | Spares Supply & Installation | JOB | 1 | 60438 | 60438 | 10878.84 | 71316.84 | 0 | 1 | 60438 | 0 | 0 | 10878.84 | 71316.84 | 0 | 0 | Water Sample Analysis As Per IS 10500 |  | Auditor | Swapnil Masane | Auditor | Job Work |  |  | No category | Approved | Auditor |  | 100 | AMC | 2025-11-16
Facility_Montek Land Spaces LLP | 17 | 0 | 20 Aug 2025 | Jones Lang Lasalle Building Operations Private Limited | Property Management Team | Admin and OH cost - Monthly basis | Month | 8 | 93000 | 744000 | 133920 | 877920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 877920 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-11-18
Facility_Montek Land Spaces LLP | 17 | 0 | 20 Aug 2025 | Jones Lang Lasalle Building Operations Private Limited | Property Management Team | Estate Manager | Month | 8 | 125000 | 1000000 | 180000 | 1180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1180000 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-11-18
Facility_Montek Land Spaces LLP | 17 | 0 | 20 Aug 2025 | Jones Lang Lasalle Building Operations Private Limited | Property Management Team | Fire and Safety Officer | Month | 8 | 75000 | 600000 | 108000 | 708000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 708000 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-11-18
Facility_Montek Land Spaces LLP | 17 | 0 | 20 Aug 2025 | Jones Lang Lasalle Building Operations Private Limited | Property Management Team | Management Fees - Monthly Basis | Month | 8 | 250000 | 2000000 | 360000 | 2360000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2360000 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-11-18
Facility_Montek Land Spaces LLP | 17 | 0 | 20 Aug 2025 | Jones Lang Lasalle Building Operations Private Limited | Property Management Team | Shift Engineer | Month | 16 | 55000 | 880000 | 158400 | 1038400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1038400 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2025-11-18
Facility_Montek Land Spaces LLP | 18 | 0 | 29 Aug 2025 | SHREERAM ENTERPRISES | HDPE pipe repair | Generator | NOS | 1 | 1500 | 1500 | 270 | 1770 | 5 | 1 | 1500 | 0 | 0 | 270 | 1770 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Utility | 2025-11-27
Facility_Montek Land Spaces LLP | 18 | 0 | 29 Aug 2025 | SHREERAM ENTERPRISES | HDPE pipe repair | Leakage Rectification | NOS | 5 | 7000 | 35000 | 6300 | 41300 | 5 | 5 | 35000 | 0 | 0 | 6300 | 41300 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Utility | 2025-11-27
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping staff - August 2025 | Days | 217 | 598.29 | 129828.93 | 23369.2 | 153198.13 | 0 | 102 | 61025.58 | 0 | 0 | 10984.6 | 72010.18 | 115 | 81187.95 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 47.0046 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping staff - July 2025 | Days | 217 | 598.29 | 129828.93 | 23369.2 | 153198.13 | 0 | 185 | 110683.65 | 0 | 0 | 19923.06 | 130606.71 | 32 | 22591.42 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 85.2535 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping staff - September 2025 | Days | 210 | 618.23 | 129828.3 | 23369.1 | 153197.4 | 0 | 152 | 93970.96 | 0 | 0 | 16914.78 | 110885.74 | 58 | 42311.66 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 72.381 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping Supervisor - August 2025 | Days | 31 | 733.39 | 22735.09 | 4092.32 | 26827.41 | 0 | 21.5 | 15767.89 | 0 | 0 | 2838.22 | 18606.11 | 9.5 | 8221.31 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 69.3548 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping Supervisor - July 2025 | Days | 31 | 733.39 | 22735.09 | 4092.32 | 26827.41 | 0 | 30.5 | 22368.4 | 0 | 0 | 4026.32 | 26394.72 | 0.5 | 432.7 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 98.3871 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 21 | 0 | 01 Sep 2025 | HP Facility Management Services Pvt Ltd | Housekeeping Manpower Services | Housekeeping Supervisor - September 2025 | Days | 30 | 757.83 | 22734.9 | 4092.28 | 26827.18 | 0 | 6 | 4546.98 | 0 | 0 | 818.46 | 5365.44 | 24 | 21461.74 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Chetan.Shilimkar | 01 Sep 2025 | 20 | Agencies | 2025-11-30
Facility_Montek Land Spaces LLP | 22 | 0 | 03 Sep 2025 | Shree Siddhivinayak Aqua Solutions | WTP outlet water testing | WTP outlet water testing | NOS | 1 | 2700 | 2700 | 486 | 3186 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3186 | WTP Water testing Drinking Water testing parameters 1.Colour 2.Odour 3.Turbidity 4.PH 5.Conducitvty 6.Total Dissolved Soild 7.Total hardness 8.calclum 9.Magnesium 10.Chlorides 11.Total Alkalinity 12.Acidlity 13.Sulphates 14.TSS 15.COD 16.BOD 17.Total Coliform 18.E Coil |  |  | Chetan.Shilimkar |  | Construction |  |  | No category | Token |  |  | 0 | Agencies | 2025-12-02
Facility_Montek Land Spaces LLP | 23 | 0 | 08 Oct 2025 | Securise Services | Security Deployment Charges | Management Fees | JOB | 1 | 44851.2 | 44851.2 | 8073.22 | 52924.42 | 5 | 0.9488 | 42554.82 | 0 | 0 | 7659.88 | 50214.7 | 0.0512 | 2709.72 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2026-01-06
Facility_Montek Land Spaces LLP | 23 | 0 | 08 Oct 2025 | Securise Services | Security Deployment Charges | Security Manpower - Nov 2025 | Days | 180 | 934.4 | 168192 | 30274.56 | 198466.56 | 5 | 164 | 153241.6 | 0 | 0 | 27583.48 | 180825.08 | 16 | 17641.48 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 91.1111 | Agencies | 2026-01-06
Facility_Montek Land Spaces LLP | 23 | 0 | 08 Oct 2025 | Securise Services | Security Deployment Charges | Security Manpower - Oct 2025 | Days | 192 | 876 | 168192 | 30274.56 | 198466.56 | 5 | 166 | 145416 | 0 | 0 | 26174.88 | 171590.88 | 26 | 26875.68 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 86.4583 | Agencies | 2026-01-06
Facility_Montek Land Spaces LLP | 23 | 0 | 08 Oct 2025 | Securise Services | Security Deployment Charges | Security Manpower - Sept 2025 | Days | 120 | 934.4 | 112128 | 20183.04 | 132311.04 | 5 | 56 | 52326.4 | 0 | 0 | 9418.76 | 61745.16 | 64 | 70565.88 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 46.6667 | Agencies | 2026-01-06
Facility_Montek Land Spaces LLP | 25 | 0 | 09 Oct 2025 | Sunshine Electricals | Flood light works | 2C x 4 Sqmm flexible copper cable - L | Rmt. | 300 | 30 | 9000 | 1620 | 10620 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 10620 |  |  |  | Chetan.Shilimkar |  | Construction |  |  | No category | Un-Approved |  |  | 0 | Agencies | 2026-01-07
Facility_Montek Land Spaces LLP | 25 | 0 | 09 Oct 2025 | Sunshine Electricals | Flood light works | 2C x 4 Sqmm flexible copper cable - M | Rmt. | 300 | 145 | 43500 | 7830 | 51330 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 51330 |  |  |  | Chetan.Shilimkar |  | Construction |  |  | No category | Un-Approved |  |  | 0 | Agencies | 2026-01-07
Facility_Montek Land Spaces LLP | 25 | 0 | 09 Oct 2025 | Sunshine Electricals | Flood light works | Halogen flood light ( 100 Watt ) - L | NOS | 12 | 500 | 6000 | 1080 | 7080 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 7080 |  |  |  | Chetan.Shilimkar |  | Construction |  |  | No category | Un-Approved |  |  | 0 | Agencies | 2026-01-07
Facility_Montek Land Spaces LLP | 25 | 0 | 09 Oct 2025 | Sunshine Electricals | Flood light works | Halogen flood light ( 100 Watt ) - M | NOS | 12 | 2150 | 25800 | 4644 | 30444 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 30444 |  |  |  | Chetan.Shilimkar |  | Construction |  |  | No category | Un-Approved |  |  | 0 | Agencies | 2026-01-07
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping staff - December 2025 | Days | 372 | 664.47 | 247182.84 | 44492.92 | 291675.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 291675.76 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping staff - February 2026 | Days | 336 | 735.66 | 247181.76 | 44492.72 | 291674.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 291674.48 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping staff - January 2026 | Days | 372 | 664.47 | 247182.84 | 44492.92 | 291675.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 291675.76 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping staff - March 2026 | Days | 372 | 664.47 | 247182.84 | 44492.92 | 291675.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 291675.76 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping staff - November 2025 | Days | 264 | 686.62 | 181267.68 | 32628.18 | 213895.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 213895.86 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping Supervisor - December 2025 | Days | 31 | 803.21 | 24899.51 | 4481.92 | 29381.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 29381.43 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping Supervisor - February 2026 | Days | 28 | 889.27 | 24899.56 | 4481.92 | 29381.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 29381.48 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping Supervisor - January 2026 | Days | 31 | 803.21 | 24899.51 | 4481.92 | 29381.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 29381.43 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping Supervisor - March 2026 | Days | 31 | 803.21 | 24899.51 | 4481.92 | 29381.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 29381.43 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 28 | 0 | 12 Nov 2025 | NORTAN FACILITY MANAGEMENT | Housekeeping staff and Supervisor | Housekeeping Supervisor - November 2025 | Days | 22 | 829.98 | 18259.56 | 3286.72 | 21546.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 21546.28 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 0 | Agencies | 2026-02-10
Facility_Montek Land Spaces LLP | 30 | 0 | 25 Nov 2025 | HP Facility Management Services Pvt Ltd | HK services ( Manpower ) for HPFMS | Housekeeping staff - November 2025 | Days | 27 | 618.23 | 16692.21 | 3004.6 | 19696.81 | 0 | 27 | 16692.21 | 0 | 0 | 3004.6 | 19696.81 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2026-02-23
Facility_Montek Land Spaces LLP | 30 | 0 | 25 Nov 2025 | HP Facility Management Services Pvt Ltd | HK services ( Manpower ) for HPFMS | Housekeeping staff - October 2025 | Days | 116 | 598.29 | 69401.64 | 12492.3 | 81893.94 | 0 | 116 | 69401.64 | 0 | 0 | 12492.3 | 81893.94 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2026-02-23
Facility_Montek Land Spaces LLP | 30 | 0 | 25 Nov 2025 | HP Facility Management Services Pvt Ltd | HK services ( Manpower ) for HPFMS | Housekeeping Supervisor - November 2025 | Days | 7 | 757.83 | 5304.81 | 954.86 | 6259.67 | 0 | 7 | 5304.81 | 0 | 0 | 954.86 | 6259.67 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2026-02-23
Facility_Montek Land Spaces LLP | 30 | 0 | 25 Nov 2025 | HP Facility Management Services Pvt Ltd | HK services ( Manpower ) for HPFMS | Housekeeping Supervisor - October 2025 | Days | 29 | 733.39 | 21268.31 | 3828.3 | 25096.61 | 0 | 29 | 21268.31 | 0 | 0 | 3828.3 | 25096.61 | 0 | 0 |  |  | Auditor | Chetan.Shilimkar | Auditor | Construction |  |  | No category | Approved | Auditor |  | 100 | Agencies | 2026-02-23