## Project_Work_Order6390174292914
Project Work Order
From 19 Nov 2020 To 20 Dec 2025
Page 1 of 1
Total Records: 11 Records 1 To 11
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per | Budget_Head | WO_Completion_Date
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Earth work Excavation Work | Backfilling using available soil | Cu.Mtrs | 721.3373 | 130 | 93773.85 | 16879.3 | 110653.15 | 5 | 721.3373 | 93773.85 | 0 | 0 | 16879.28 | 110653.13 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Earth work Excavation Work | Excavation in Hard Murum & Soft Rock | Cu.Mtrs | 47.3888 | 90 | 4264.99 | 767.7 | 5032.69 | 5 | 47.3888 | 4264.99 | 0 | 0 | 767.7 | 5032.69 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Earth work Excavation Work | Excavation In Soft Soil | Cu.Mtrs | 1055.6172 | 90 | 95005.55 | 17101 | 112106.55 | 5 | 1055.6172 | 95005.55 | 0 | 0 | 17101 | 112106.55 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Brick Work Brickwork | FLY ASH Brick - 450 MM (L+M) | Cu.Mtrs | 52.4 | 2300 | 120520 | 21693.6 | 142213.6 | 5 | 52.4 | 120520 | 0 | 0 | 21693.6 | 142213.6 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | Civil Work | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Brick Work Brickwork | Fly Ash Brick Masonry 230mm Thk | SQMT | 38.08 | 1225 | 46648 | 8396.64 | 55044.64 | 5 | 38.08 | 46648 | 0 | 0 | 8396.64 | 55044.64 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | RCC Work RCC Civil Works | PCC M15 grade | Cu.Mtrs | 103.5608 | 4500 | 466023.6 | 83884.24 | 549907.84 | 5 | 103.5608 | 466023.6 | 0 | 0 | 83884.26 | 549907.86 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 30 May 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | RCC Work RCC Civil Works | RCC M25 Grade Concrete | Cu.Mtrs | 167.463 | 7200 | 1205733.6 | 217032.04 | 1422765.64 | 5 | 167.463 | 1205733.6 | 0 | 0 | 217032.04 | 1422765.64 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | RCC Work RCC Civil Works | Shuttering Work | SQM | 712.2375 | 975 | 694431.56 | 124997.68 | 819429.24 | 5 | 712.2375 | 694431.56 | 0 | 0 | 124997.7 | 819429.26 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Internal Plaster work Internal Plastering works | Single coat- Back coat Plaster | SQMT | 365.1665 | 690 | 251964.89 | 45353.68 | 297318.57 | 5 | 365.1665 | 251964.89 | 0 | 0 | 45353.68 | 297318.57 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 02 Jun 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | Earth work Excavation Work | Surface preparation for PCC, Soling | Sqm | 1226.0065 | 40 | 49040.26 | 8827.24 | 57867.5 | 5 | 1226.0065 | 49040.26 | 0 | 0 | 8827.26 | 57867.52 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31
MAHA TRADE MARKET(MTM) | 88 | 0 | 02 Aug 2024 | SHREE SADGURU CONSTRUCTION | RCC Work RCC Civil Works | TMT FE 500 steel | Mtr. | 10.0574 | 72000 | 724132.8 | 130343.9 | 854476.7 | 5 | 10.0574 | 724132.8 | 0 | 0 | 130343.9 | 854476.7 | 0 | 0 |  |  | Auditor | Kishor Sanghai | Auditor | Construction |  |  | No category | Foreclose | Auditor | 18 Dec 2025 | 100 |  | 2025-08-31